## Test Plan
Module Name | Objective | Scope | Test Type | Entry Criteria | Exit Criteria | Risks | Resources
Login Module | Validate user login functionality | Functional Testing | Smoke, Regression | Build deployed | All test cases passed | Environment instability | QA Team

## Test Scenarios
Scenario ID | Scenario Description | Preconditions
TS001 | Verify user can login with valid credentials | User has valid credentials

## Test Cases
Test Case ID | Description | Preconditions | Steps | Expected Result | Actual Result | Status | Comments
TC_AUTH_001 | Verify token is generated with valid credentials | API endpoint https://restful-booker.herokuapp.com/auth is up and accessible | 1. Send POST request with valid JSON body: | Status code = 200 | Status code = 200 | PASS
|  |  | { "username": "admin", "password": "password123" } | Response body contains token field | Response body contains token field
|  |  | 2. Content-Type header = application/json | Token value is a non-empty string | Token value is a non-empty string
TC_AUTH_002 | Verify API returns error with invalid username | API endpoint https://restful-booker.herokuapp.com/auth is up and accessible | 1. Send POST request with { "username": "wrong", "password": "password123" } | Status code = 200 or 4xx | Status code = 200 | PASS
|  |  |  | Response does not contain token or returns error message | Response body returns error message "reason": "Bad credentials"
TC_AUTH_003 | Verify API returns error with invalid password | API endpoint https://restful-booker.herokuapp.com/auth is up and accessible | 1. Send POST request with { "username": "admin", "password": "wrongpass" } | Should not generate token; proper error message returned | Status code = 200 | PASS
Response body returns error message "reason": "Bad credentials"
TC_AUTH_004 | Verify API returns error when username field is missing | API endpoint https://restful-booker.herokuapp.com/auth is up and accessible | 1. Send POST request with { "": "password123" } | Status code = 400 | Status code = 200 | PASS
|  |  |  | Proper error message returned | Response body returns error message "reason": "Bad credentials"
TC_AUTH_005 | Verify API returns error when Content-Type header is missing | API endpoint https://restful-booker.herokuapp.com/auth is up and accessible | 1. Send POST request without Content-Type header | Should return 415 Unsupported Media Type or relevant error | Status code = 200 | PASS
Response body returns error message "reason": "Bad credentials"
TC_BOOKING_001 | Verify returns IDs of all booking | API endpoint https://restful-booker.herokuapp.com/booking is up and accessible | 1. Send Get Request with booking endpoint | Should Return IDs of all booking | Status Code=200 | PASS
Returned IDs of all Booking
TC_BOOKING_002 | Verify returns specific booking based upon booking ID provided | API endpoint https://restful-booker.herokuapp.com/booking is up and accessible | 1. Send Get Request with booking ID 142 | Should return the booking details of ID 142 | Status Code=200 | PASS
Returned the Booking Details for ID 142
TC_BOOKING_003 | Verify if it creates a new booking | API endpoint https://restful-booker.herokuapp.com/booking is up and accessible | 1. Send a Post Request with valid json body "{ "firstname" : "Swag", "lastname" : "Create", "totalprice" : 111, "depositpaid" : true, "bookingdates" : { "checkin" : "2018-01-01", "checkout" : "2019-01-01" }" | Should Create a new booking with the data provided | Status code=200 | PASS
|  |  | 2. Add Header 'Content type: application/json' |  | Created New Booking with the provided data
TC_BOOKING_004 | Verify if sucessfully updates ID 2538 | API endpoint https://restful-booker.herokuapp.com/booking is up and accessible | 1. Send PUT request with Valid Json Body and Update Lunch in place of superbowls | Should Successfully update the changes | Status Code=200 | PASS
|  |  | 2. Generate and Pass the Token |  | Successfully updated the lunch in place of superbowls
TC_BOOKING_005 | Verify if it Deletes a booking ID | API endpoint https://restful-booker.herokuapp.com/booking is up and accessible | 1. Send Delete request with ID | Should successfully Delete the ID | Successfully Deleted the ID
2. Generate and Pass the Token

## RTM
Requirement ID | Requirement Description | Linked Test Case IDs | Status
REQ001 | User should be able to login successfully | TC001 | Tested

## Defect Tracker
Bug ID | Module | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To
BUG001 | Login | High | P1 | Enter invalid password | Show error | App crashes | Open | Developer A

## Execution Report
Test Case ID | Execution Date | Tester | Result | Defects Logged
TC001 | 2025-11-06 | Swagath | Pass | None

## DSR
Date | Tester Name | Modules Tested | Test Cases Executed | Bugs Found | Blockers
2025-11-06 | Swagath | Login, Signup | 10 | 2 | API response delay

## Sprint Summary
Sprint | Total Test Cases | Passed | Failed | Blocked | Defects Logged
Sprint 5 | 100 | 90 | 8 | 2 | 15

## Closure Report
Summary | Total Cases | Passed | Pass Rate | Major Bugs | Risks | Sign-off
Project completed successfully | 500 | 480 | 96% | 3 | Minor API delays | Approved

## Automation Report
Test Suite | Environment | Pass % | Fail % | Execution Time | Report Link
API Automation | Staging | 95 | 5 | 10 mins | RestfulBookerReport.html